## Overview
16 Week Atomic Action Plan
Traffic Radius enterprise SEO evidence register ? professional V18-compatible v19 edition
Control | Canonical value
Evidence as of | 2026-07-15
Approved domain | kakawachocolates.com.au
Run | KAKAWA-ENT-20260715
Evidence status | EVIDENCE-LINKED
Decision | Review and approve before implementation.
Record count | 16
Release class | REVIEW READY
Quality gate | Value
Evidence-linked | 1
Approval required | 0
Fabricated substitutes | 0

## Register
16 Week Atomic Action Plan
Canonical values only. Unavailable evidence is labelled explicitly; no estimates or fabricated substitutes.
ID | Week | Action | Owner | Dependency | Effort | KPI | Risk | Approval
A-001 | 1 | Approve the evidence boundary and unavailable-source register | Agency admin |  | 4h | Gate 1 decision recorded | low | agency_admin
A-002 | 1 | Connect and validate GSC, GA4, SEMrush and PageSpeed in staging | Analyst | A-001 | 12h | Four source readiness checks | moderate | analyst
A-003 | 2 | Reconcile crawl inventory, sitemaps, redirects and canonical graph | Technical SEO | A-001 | 16h | Zero graph safety failures | high | agency_admin
A-004 | 3 | Resolve high-confidence HTTP, title, meta and H1 findings | SEO + Engineering | A-003 | 24h | P1 finding count reduced | moderate | analyst
A-005 | 3 | Define analytics events, conversion definitions and baseline capture | Analytics | A-002 | 16h | Approved measurement dictionary | moderate | analyst
A-006 | 5 | Confirm canonical topic-to-URL map and cannibalisation decisions | SEO Strategist | A-002, A-004 | 16h | One target per approved intent | low | analyst
A-007 | 6 | Design evidence-supported internal-link modules | SEO + UX | A-006 | 12h | Approved link specification | low | analyst
A-008 | 7 | Stage metadata and heading changes on a representative template set | Engineering | A-004, A-006 | 20h | Template QA pass rate | moderate | analyst
A-009 | 8 | Review page-specific schema candidates against verified facts | Technical SEO | A-006 | 12h | Zero unsupported schema properties | high | agency_admin
A-010 | 9 | Editorially review the first three evidence-bound content refreshes | Content Lead | A-006 | 18h | Three human-approved drafts | low | client_reviewer
A-011 | 10 | Editorially review the remaining distinct content refreshes | Content Lead | A-010 | 18h | 3 additional approvals | low | client_reviewer
A-012 | 11 | Import and reconcile GBP/BrightLocal evidence before local changes | Local SEO | A-002 | 10h | Local fact reconciliation | moderate | analyst
A-013 | 11 | Run accessibility and conversion-path review with analytics baselines | UX + Analytics | A-005, A-008 | 18h | Approved experiment backlog | low | analyst
A-014 | 13 | Execute staging crawl, link, canonical, schema and render QA | QA | A-007, A-008, A-009, A-011 | 20h | Zero Critical or High QA failures | moderate | agency_admin
A-015 | 14 | Reconcile UI, workbooks, reports, deck and manifest | QA | A-014 | 12h | All canonical counts match | low | analyst
A-016 | 16 | Complete Gate 2, final QA and controlled production decision | Agency admin + client | A-015 | 8h | Documented approve or revise decision | high | agency_admin