## Read Me
Kakawa 16-Week Canonical Action Plan · v19
Evidence as of 2026-07-15 · Action IDs are authoritative across every derivative.
Control | Meaning
Canonical source | The Action Plan sheet; changes create a versioned record.
Approval classes | Admin approval is required for redirects, canonicals, robots, schema and disavow candidates.
External execution | Not performed by this application.
Private baselines | Remain unavailable until GSC/GA4/SEMrush connections are approved.
Status values | Not started, Ready, In progress, Blocked, Review, Approved, Complete
Priority | P1–P4 reflects impact, confidence, reach, criticality, dependencies and effort.
Run | KAKAWA-ENT-20260715

## Action Plan
Canonical action plan
Owners, dependencies, effort, KPIs, evidence, risk and approval controls.
ID | Phase | Week start | Week end | Priority | Action | Owner | Dependencies | Effort | KPI | Approval class | Status | Evidence | Confidence | Duration | Implementation risk | Notes
A-001 | Foundation | 1 | 1 | P1 | Approve the evidence boundary and unavailable-source register | Agency admin | None | 3h | Gate 1 scope decision recorded | agency_admin | Ready | EV-0001 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-002 | Foundation | 1 | 1 | P1 | Confirm the approved .com.au domain and exclusion rules | Technical SEO | A-001 | 3h | Zero wrong-domain records | agency_admin | Ready | EV-0001 | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.
A-003 | Foundation | 1 | 1 | P2 | Reconcile discovered, fetched and normalized URL counts | Analyst | A-002 | 4h | One canonical inventory count | analyst | Ready | EV-0001 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-004 | Evidence | 2 | 2 | P1 | Connect and validate Google Search Console in staging | Analyst | A-001 | 5h | GSC availability check passes | analyst | Not started | EV-UNAVAILABLE-GSC | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.
A-005 | Evidence | 2 | 2 | P1 | Connect and validate GA4 plus conversion definitions | Analytics | A-001 | 6h | GA4 event dictionary approved | analyst | Not started | EV-UNAVAILABLE-GA4 | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.
A-006 | Evidence | 2 | 2 | P2 | Connect SEMrush and PageSpeed or preserve truthful unavailable states | Analyst | A-001 | 5h | Two source readiness decisions | analyst | Not started | EV-UNAVAILABLE-SEMRUSH, EV-UNAVAILABLE-PAGESPEED | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-007 | Technical | 3 | 3 | P1 | Validate HTTP status distribution and error-page ownership | Technical SEO | A-003 | 6h | Every error URL assigned a disposition | analyst | Not started | EV-0155, EV-0199, EV-0204, EV-0205, EV-0208, EV-0209, EV-0219, EV-0222 | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.
A-008 | Technical | 3 | 3 | P1 | Validate redirect chains and reject redirect loops | Engineering | A-007 | 7h | Zero redirect loops | agency_admin | Not started | EV-0155, EV-0199, EV-0204, EV-0205, EV-0208, EV-0209, EV-0219, EV-0222 | 100% | 1 | high | Advisory only; no external system changes are executed by the studio.
A-009 | Technical | 3 | 3 | P1 | Validate canonical graph targets against approved-domain pages | Technical SEO | A-007 | 7h | Zero unsafe canonical targets | agency_admin | Not started | EV-0155, EV-0199, EV-0204, EV-0205, EV-0208, EV-0209, EV-0219, EV-0222 | 100% | 1 | high | Advisory only; no external system changes are executed by the studio.
A-010 | On-page | 4 | 4 | P1 | Resolve missing or weak title tags on priority templates | SEO + Content | A-007 | 8h | Priority title review completed | analyst | Not started | EV-0223, EV-0226, EV-0231, EV-0235, EV-0241, EV-0258, EV-0259, EV-0261 | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.
A-011 | On-page | 4 | 4 | P1 | Resolve missing meta descriptions on priority templates | SEO + Content | A-010 | 8h | Priority meta review completed | analyst | Not started | EV-0223, EV-0226, EV-0231, EV-0235, EV-0241, EV-0258, EV-0259, EV-0261 | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.
A-012 | On-page | 4 | 4 | P1 | Resolve missing, multiple or duplicated H1 patterns | SEO + Engineering | A-010 | 6h | Priority H1 review completed | analyst | Not started | EV-0223, EV-0226, EV-0231, EV-0235, EV-0241, EV-0258, EV-0259, EV-0261 | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.
A-013 | Ecommerce | 5 | 5 | P1 | Review product template indexability, titles and canonical behavior | Technical SEO | A-009 | 8h | Product template QA passes | agency_admin | Not started | EV-0155, EV-0199, EV-0204, EV-0205, EV-0208, EV-0209, EV-0219, EV-0222 | 100% | 1 | high | Advisory only; no external system changes are executed by the studio.
A-014 | Ecommerce | 5 | 5 | P2 | Review collection pagination and duplicate-route behavior | Technical SEO | A-009 | 7h | Pagination decisions documented | agency_admin | Not started | EV-0155, EV-0199, EV-0204, EV-0205, EV-0208, EV-0209, EV-0219, EV-0222 | 100% | 1 | high | Advisory only; no external system changes are executed by the studio.
A-015 | Ecommerce | 5 | 5 | P2 | Create a verified fact pack before proposing Product schema | SEO + Merchandising | A-013 | 8h | Zero unsupported schema properties | agency_admin | Not started | EV-0001 | 100% | 1 | high | Advisory only; no external system changes are executed by the studio.
A-016 | Evidence | 6 | 6 | P2 | Import backlink evidence before authority scoring or outreach | Off-page SEO | A-006 | 6h | Backlink source validated or unavailable | analyst | Not started | EV-0001 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-017 | Evidence | 6 | 6 | P2 | Import GBP or BrightLocal evidence before local recommendations | Local SEO | A-006 | 5h | Local fact source validated or unavailable | analyst | Not started | EV-0001 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-018 | Evidence | 6 | 6 | P2 | Validate analytics and tag implementation before CRO claims | Analytics | A-005 | 7h | Tracking audit decision recorded | analyst | Not started | EV-UNAVAILABLE-GA4 | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.
A-019 | Architecture | 7 | 7 | P1 | Approve one accountable URL for each of 20 content intents | SEO Strategist | A-004, A-006 | 8h | 20 unique target decisions | analyst | Not started | EV-0001, EV-FACT-02, EV-FACT-03, EV-0011, EV-FACT-02, EV-0006, EV-FACT-02, EV-0017, EV-FACT-02, EV-0008, EV-FACT-02, EV-0018, EV-FACT-02, EV-0081, EV-FACT-02, EV-0009, EV-FACT-02, EV-0022, EV-FACT-02, EV-FACT-03 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-020 | Architecture | 7 | 7 | P2 | Document duplicate-title and H1 clusters for consolidation review | SEO Strategist | A-019 | 6h | Every duplicate cluster has a decision | analyst | Not started | EV-0223, EV-0226, EV-0231, EV-0235, EV-0241, EV-0258, EV-0259, EV-0261 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-021 | Architecture | 7 | 7 | P2 | Freeze the URL architecture map and cannibalization ledger | Agency admin | A-019, A-020 | 5h | Gate 1 architecture approval | agency_admin | Not started | EV-0001, EV-FACT-02, EV-FACT-03, EV-0011, EV-FACT-02, EV-0006, EV-FACT-02, EV-0017, EV-FACT-02, EV-0008, EV-FACT-02, EV-0018, EV-FACT-02, EV-0081, EV-FACT-02, EV-0009, EV-FACT-02, EV-0022, EV-FACT-02, EV-FACT-03 | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.
A-022 | Internal links | 8 | 8 | P2 | Validate observed internal-link graph and orphan risk | Technical SEO | A-021 | 7h | Link graph reconciliation passes | analyst | Not started | EV-0155, EV-0199, EV-0204, EV-0205, EV-0208, EV-0209, EV-0219, EV-0222 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-023 | Internal links | 8 | 8 | P2 | Approve parent-child collection and product link candidates | SEO + UX | A-022 | 7h | Approved contextual link map | analyst | Not started | EV-0001, EV-FACT-02, EV-FACT-03, EV-0011, EV-FACT-02, EV-0006, EV-FACT-02, EV-0017, EV-FACT-02, EV-0008, EV-FACT-02, EV-0018, EV-FACT-02, EV-0081, EV-FACT-02, EV-0009, EV-FACT-02, EV-0022, EV-FACT-02, EV-FACT-03 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-024 | Internal links | 8 | 8 | P3 | Review breadcrumbs and navigation labels for descriptive anchors | UX + Engineering | A-022 | 6h | Navigation review completed | analyst | Not started | EV-0001 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-025 | Implementation | 9 | 9 | P1 | Stage title and meta changes on representative templates | Engineering | A-010, A-011 | 10h | Template metadata QA passes | analyst | Not started | EV-0223, EV-0226, EV-0231, EV-0235, EV-0241, EV-0258, EV-0259, EV-0261 | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.
A-026 | Implementation | 9 | 9 | P1 | Stage H1 and heading hierarchy changes | Engineering | A-012 | 8h | Heading accessibility QA passes | analyst | Not started | EV-0223, EV-0226, EV-0231, EV-0235, EV-0241, EV-0258, EV-0259, EV-0261 | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.
A-027 | Implementation | 9 | 9 | P2 | Run visual, mobile and structured-data regression checks | QA | A-025, A-026 | 8h | Zero Critical or High regressions | agency_admin | Not started | EV-0155, EV-0199, EV-0204, EV-0205, EV-0208, EV-0209, EV-0219, EV-0222 | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.
A-028 | Content | 10 | 10 | P2 | Editorially review content assets 01-03 | Content Lead | A-021 | 9h | Three evidence-led drafts approved or revised | client_reviewer | Not started | EV-0001, EV-FACT-02, EV-FACT-03, EV-0011, EV-FACT-02, EV-0006, EV-FACT-02, EV-0017, EV-FACT-02, EV-0008, EV-FACT-02, EV-0018, EV-FACT-02, EV-0081, EV-FACT-02, EV-0009, EV-FACT-02, EV-0022, EV-FACT-02, EV-FACT-03 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-029 | Content | 10 | 10 | P2 | Editorially review content assets 04-06 | Content Lead | A-028 | 9h | Three additional drafts approved or revised | client_reviewer | Not started | EV-0001, EV-FACT-02, EV-FACT-03, EV-0011, EV-FACT-02, EV-0006, EV-FACT-02, EV-0017, EV-FACT-02, EV-0008, EV-FACT-02, EV-0018, EV-FACT-02, EV-0081, EV-FACT-02, EV-0009, EV-FACT-02, EV-0022, EV-FACT-02, EV-FACT-03 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-030 | Content | 10 | 10 | P2 | Run claim, link and similarity checks for assets 01-06 | QA | A-028, A-029 | 6h | Zero unsupported or cannibalizing drafts | analyst | Not started | EV-0001, EV-FACT-02, EV-FACT-03, EV-0011, EV-FACT-02, EV-0006, EV-FACT-02, EV-0017, EV-FACT-02, EV-0008, EV-FACT-02, EV-0018, EV-FACT-02, EV-0081, EV-FACT-02, EV-0009, EV-FACT-02, EV-0022, EV-FACT-02, EV-FACT-03 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-031 | Content | 11 | 11 | P2 | Editorially review content assets 07-11 | Content Lead | A-030 | 12h | Five drafts approved or revised | client_reviewer | Not started | EV-0001, EV-FACT-02, EV-FACT-03, EV-0011, EV-FACT-02, EV-0006, EV-FACT-02, EV-0017, EV-FACT-02, EV-0008, EV-FACT-02, EV-0018, EV-FACT-02, EV-0081, EV-FACT-02, EV-0009, EV-FACT-02, EV-0022, EV-FACT-02, EV-FACT-03 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-032 | Content | 11 | 11 | P2 | Editorially review content assets 12-15 | Content Lead | A-031 | 10h | Four drafts approved or revised | client_reviewer | Not started | EV-0001, EV-FACT-02, EV-FACT-03, EV-0011, EV-FACT-02, EV-0006, EV-FACT-02, EV-0017, EV-FACT-02, EV-0008, EV-FACT-02, EV-0018, EV-FACT-02, EV-0081, EV-FACT-02, EV-0009, EV-FACT-02, EV-0022, EV-FACT-02, EV-FACT-03 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-033 | Content | 11 | 11 | P2 | Run claim, link and similarity checks for assets 07-15 | QA | A-031, A-032 | 8h | Zero unsupported or cannibalizing drafts | analyst | Not started | EV-0001, EV-FACT-02, EV-FACT-03, EV-0011, EV-FACT-02, EV-0006, EV-FACT-02, EV-0017, EV-FACT-02, EV-0008, EV-FACT-02, EV-0018, EV-FACT-02, EV-0081, EV-FACT-02, EV-0009, EV-FACT-02, EV-0022, EV-FACT-02, EV-FACT-03 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-034 | Content | 12 | 12 | P2 | Editorially review content assets 16-20 | Content Lead | A-033 | 12h | Five drafts approved or revised | client_reviewer | Not started | EV-0001, EV-FACT-02, EV-FACT-03, EV-0011, EV-FACT-02, EV-0006, EV-FACT-02, EV-0017, EV-FACT-02, EV-0008, EV-FACT-02, EV-0018, EV-FACT-02, EV-0081, EV-FACT-02, EV-0009, EV-FACT-02, EV-0022, EV-FACT-02, EV-FACT-03 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-035 | Content | 12 | 12 | P2 | Validate accessibility, reading flow and calls to action | UX + Content | A-034 | 8h | Content accessibility checklist passes | analyst | Not started | EV-0001, EV-FACT-02, EV-FACT-03, EV-0011, EV-FACT-02, EV-0006, EV-FACT-02, EV-0017, EV-FACT-02, EV-0008, EV-FACT-02, EV-0018, EV-FACT-02, EV-0081, EV-FACT-02, EV-0009, EV-FACT-02, EV-0022, EV-FACT-02, EV-FACT-03 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-036 | Content | 12 | 12 | P2 | Complete Gate 2 content and implementation decision | Agency admin + client | A-034, A-035 | 5h | Gate 2 decision recorded | agency_admin | Not started | EV-0001, EV-FACT-02, EV-FACT-03, EV-0011, EV-FACT-02, EV-0006, EV-FACT-02, EV-0017, EV-FACT-02, EV-0008, EV-FACT-02, EV-0018, EV-FACT-02, EV-0081, EV-FACT-02, EV-0009, EV-FACT-02, EV-0022, EV-FACT-02, EV-FACT-03 | 100% | 1 | high | Advisory only; no external system changes are executed by the studio.
A-037 | CRO | 13 | 13 | P3 | Map priority conversion journeys after GA4 validation | UX + Analytics | A-018 | 8h | Approved journey map | analyst | Not started | EV-UNAVAILABLE-GA4, EV-0001 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-038 | CRO | 13 | 13 | P3 | Create an evidence-supported experiment backlog | UX + Analytics | A-037 | 8h | Experiments have baselines and owners | analyst | Not started | EV-UNAVAILABLE-GA4, EV-0001 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-039 | CRO | 13 | 13 | P3 | Review forms, contact routes and mobile interaction states | UX + QA | A-037 | 7h | Interaction audit completed | analyst | Not started | EV-0001 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-040 | Release | 14 | 14 | P1 | Implement approved redirects and canonicals in staging only | Engineering | A-008, A-009, A-036 | 12h | Staging graph validation passes | agency_admin | Not started | EV-0155, EV-0199, EV-0204, EV-0205, EV-0208, EV-0209, EV-0219, EV-0222 | 100% | 1 | high | Advisory only; no external system changes are executed by the studio.
A-041 | Release | 14 | 14 | P1 | Implement approved metadata, headings and internal links | Engineering | A-027, A-036 | 12h | Staging page QA passes | analyst | Not started | EV-0223, EV-0226, EV-0231, EV-0235, EV-0241, EV-0258, EV-0259, EV-0261 | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.
A-042 | Release | 14 | 14 | P1 | Deploy only approved page-specific schema candidates | Engineering | A-015, A-036 | 8h | Zero unsupported schema properties | agency_admin | Not started | EV-0001 | 100% | 1 | high | Advisory only; no external system changes are executed by the studio.
A-043 | Validation | 15 | 15 | P1 | Re-crawl staging and reconcile every normalized URL | QA | A-040, A-041, A-042 | 10h | Canonical inventory reconciliation passes | analyst | Not started | EV-0155, EV-0199, EV-0204, EV-0205, EV-0208, EV-0209, EV-0219, EV-0222 | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.
A-044 | Validation | 15 | 15 | P1 | Re-run link, redirect, canonical, schema and domain safety gates | QA | A-043 | 10h | Zero Critical or High QA failures | agency_admin | Not started | EV-0155, EV-0199, EV-0204, EV-0205, EV-0208, EV-0209, EV-0219, EV-0222 | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.
A-045 | Validation | 15 | 15 | P2 | Render and inspect XLSX, DOCX, PPTX, PDF and HTML outputs | QA | A-044 | 8h | All client artifacts open and render | analyst | Not started | EV-0001 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-046 | Approval | 16 | 16 | P1 | Reconcile UI, workbooks, reports, deck and manifest | QA | A-045 | 7h | All canonical counts match | analyst | Not started | EV-0001 | 100% | 1 | low | Advisory only; no external system changes are executed by the studio.
A-047 | Approval | 16 | 16 | P1 | Record final agency and client release decisions | Agency admin + client | A-046 | 4h | Approve or revise decision recorded | agency_admin | Not started | EV-0001 | 100% | 1 | high | Advisory only; no external system changes are executed by the studio.
A-048 | Approval | 16 | 16 | P2 | Archive checksums, restore evidence and post-release monitoring plan | Agency admin | A-047 | 5h | Recovery and monitoring handoff accepted | agency_admin | Not started | EV-0001 | 100% | 1 | moderate | Advisory only; no external system changes are executed by the studio.

## 16-Week Gantt
16-week Gantt
Formula-backed schedule derived from canonical week start and end fields.
ID | Action | Start | End | Owner | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
A-001 | Approve the evidence boundary and unavailable-source register | 1 | 1 | Agency admin | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-002 | Confirm the approved .com.au domain and exclusion rules | 1 | 1 | Technical SEO | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-003 | Reconcile discovered, fetched and normalized URL counts | 1 | 1 | Analyst | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-004 | Connect and validate Google Search Console in staging | 2 | 2 | Analyst | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-005 | Connect and validate GA4 plus conversion definitions | 2 | 2 | Analytics | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-006 | Connect SEMrush and PageSpeed or preserve truthful unavailable states | 2 | 2 | Analyst | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-007 | Validate HTTP status distribution and error-page ownership | 3 | 3 | Technical SEO | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-008 | Validate redirect chains and reject redirect loops | 3 | 3 | Engineering | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-009 | Validate canonical graph targets against approved-domain pages | 3 | 3 | Technical SEO | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-010 | Resolve missing or weak title tags on priority templates | 4 | 4 | SEO + Content | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-011 | Resolve missing meta descriptions on priority templates | 4 | 4 | SEO + Content | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-012 | Resolve missing, multiple or duplicated H1 patterns | 4 | 4 | SEO + Engineering | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-013 | Review product template indexability, titles and canonical behavior | 5 | 5 | Technical SEO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-014 | Review collection pagination and duplicate-route behavior | 5 | 5 | Technical SEO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-015 | Create a verified fact pack before proposing Product schema | 5 | 5 | SEO + Merchandising | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-016 | Import backlink evidence before authority scoring or outreach | 6 | 6 | Off-page SEO | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-017 | Import GBP or BrightLocal evidence before local recommendations | 6 | 6 | Local SEO | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-018 | Validate analytics and tag implementation before CRO claims | 6 | 6 | Analytics | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-019 | Approve one accountable URL for each of 20 content intents | 7 | 7 | SEO Strategist | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-020 | Document duplicate-title and H1 clusters for consolidation review | 7 | 7 | SEO Strategist | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-021 | Freeze the URL architecture map and cannibalization ledger | 7 | 7 | Agency admin | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-022 | Validate observed internal-link graph and orphan risk | 8 | 8 | Technical SEO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-023 | Approve parent-child collection and product link candidates | 8 | 8 | SEO + UX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-024 | Review breadcrumbs and navigation labels for descriptive anchors | 8 | 8 | UX + Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-025 | Stage title and meta changes on representative templates | 9 | 9 | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-026 | Stage H1 and heading hierarchy changes | 9 | 9 | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-027 | Run visual, mobile and structured-data regression checks | 9 | 9 | QA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-028 | Editorially review content assets 01-03 | 10 | 10 | Content Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
A-029 | Editorially review content assets 04-06 | 10 | 10 | Content Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
A-030 | Run claim, link and similarity checks for assets 01-06 | 10 | 10 | QA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
A-031 | Editorially review content assets 07-11 | 11 | 11 | Content Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
A-032 | Editorially review content assets 12-15 | 11 | 11 | Content Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
A-033 | Run claim, link and similarity checks for assets 07-15 | 11 | 11 | QA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
A-034 | Editorially review content assets 16-20 | 12 | 12 | Content Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
A-035 | Validate accessibility, reading flow and calls to action | 12 | 12 | UX + Content | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
A-036 | Complete Gate 2 content and implementation decision | 12 | 12 | Agency admin + client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
A-037 | Map priority conversion journeys after GA4 validation | 13 | 13 | UX + Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
A-038 | Create an evidence-supported experiment backlog | 13 | 13 | UX + Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
A-039 | Review forms, contact routes and mobile interaction states | 13 | 13 | UX + QA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
A-040 | Implement approved redirects and canonicals in staging only | 14 | 14 | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
A-041 | Implement approved metadata, headings and internal links | 14 | 14 | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
A-042 | Deploy only approved page-specific schema candidates | 14 | 14 | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
A-043 | Re-crawl staging and reconcile every normalized URL | 15 | 15 | QA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
A-044 | Re-run link, redirect, canonical, schema and domain safety gates | 15 | 15 | QA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
A-045 | Render and inspect XLSX, DOCX, PPTX, PDF and HTML outputs | 15 | 15 | QA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
A-046 | Reconcile UI, workbooks, reports, deck and manifest | 16 | 16 | QA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
A-047 | Record final agency and client release decisions | 16 | 16 | Agency admin + client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
A-048 | Archive checksums, restore evidence and post-release monitoring plan | 16 | 16 | Agency admin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1

## Dashboard
Delivery dashboard
Formula-backed counts update when canonical action statuses and priorities change.
Priority | Actions | Status | Actions
P1 | 21 | Not started | 45
P2 | 23 | Ready | 3
P3 | 4 | In progress | 0
P4 | 0 | Blocked | 0
|  | Review | 0
|  | Complete | 0